## Voorbeeld1
EAC = AC + ETC |  | EAC = | How much you have spent |  |  | https://www.youtube.com/watch?v=ttMLHqbub8A&list=PL13IJTeX9RPWIdvbVjOBthLtZe_hbMws5&index=10
+ How much you predict you will spend to complete the project
2.5 | 2.5 | Dag 3 Pv3=10 euro |  |  | BAC Budget at completion |  |  | 40 | euro |  | EV |  |  | euro | CPI (EV/AC) | SPI (EV/PV)
2.5 | 2.5 |  |  |  | PV1 | 10 | euro |  | EV1 = % COMPLEET x PV1 | 100% | 10 | euro | AC1 | 12 | 0.83333 | 1
2.5 | 2.5 | Dag 4 Pv4=10 euro |  |  | PV2 | 10 | euro |  | EV1 = % COMPLEET x PV2 | 75% | 7.5 | euro | AC2 | 10 | 0.75 | 0.75
2.5 | 2.5 |  |  |  | PV(1+2) | 20 |  |  | CUMULATIVE EV(1+2) |  | 17.5 |  | AC (1+2) | 22 | 0.79545 | 0.875
[5 empty] | PVC | [9 empty] | CPIC | SPIC
remaining work cost | ETC | 22.5 | 37.5 euro | (first EAC formula) | EAC BASED on a brand new bottum-up estimate for the work remaining
Er zijn 4 EAC types |  |  |  | (first EAC formula) | EAC = AC +(BRAND-NEW BOTTUM UP ETC)
ASSUME ETC IS 37,50
|  |  |  | (AC = 22 euro) | EAC = 22 euro + (37.50) = 59.50 euro
|  |  |  | (second EAC formula) | EAC ASSUMING the CURRENT Cost PERFORMANCE WILL CONTINUE INTO THE FUTURE THROUGHOUT THE PROJECT TILL PROJECT END
CUMULATIVE CPI WILL REMAIN CONSTANT
EAC = BAC/ CUMULATIVE CPI
[5 empty] | EAC = 40 euro/0.8 |  | 50 | euro
|  |  |  | (third EAC formula) | EAC ASSUMING THE ORIGINAL BUDGET FOR THE REMAINING WORK WILL REMAIN INTACT
EAC ASSUMING THAT WORK REMAINING WILL BE COMPLETED AT THE BUDGETED RATE
EAC = AC + (BAC - EV)
EAC = 22 euro + (40 - 17.50) = 44.50 euro
|  |  |  | (forth EAC formula) | EAC ASSUMING THE CPI AND SPI ARE RELEVANT AND WILL WEIGH IN TH GIVE THE FINAL PROJECT PICTURE
EAC = AC + [(BAC - EV)/(SPIc x CPIc)]
EAC = 22 + (40 - 17.50)/(0.875x0.8)
|  |  |  | worse than third | EAC= | 54.14 euro

## Voorbeeld2
| Earned Value Management REVISITED |  |  |  | https://www.youtube.com/watch?v=sEju-I_sXlM&list=PL13IJTeX9RPWIdvbVjOBthLtZe_hbMws5&index=12
cost per hour | DAY 1 BUDGET = 50 euro | DAY 1 BUDGET = 50 euro | DAY 1 BUDGET = 50 euro | DAY 1 BUDGET = 50 euro | Total Budget for the project is 200 euro
6.25 | 25 | 25 | 25 | 25
| 25 | 25 | 25 | 25
voorbeeld = wall painting in yellow, green, pink and blue
| PV |  | EV | AC
| The value of work scheduled to be done within a SPECIFIC time period | % COMPLETE the amount of work actually completed | The value of work accomplished within the specific time period | How much I paid for the work accomplished within the specific time period | CPI (EV/AC) | SPI (EV/PV) | CV (EV-AC) | SV (EV-PV)
DAY 1 | 50 | 100% | 50 | 61 | 0.81967 | 1 | -11 | 0
DAY 2 | 50 | 50% | 25 | 30 | 0.83333 | 0.5 | -5 | -25
DAY 4 |  |  |  |  | #DIV/0! | #DIV/0! | 0 | 0
CUMULATIVE | 100 | 37.5% | 75 | 91 | 0.82418 | 0.75 | -16 | -25
END OF DAY 1
| DAY 1 budget = 50 euro | DAY 1 budget = 50 euro | DAY 1 budget = 50 euro | DAY 1 budget = 50 euro | TOTAL BUDGET FOR THE PROJECT IS 200 EURO
| DONE | DONE | DONE | 4
| DONE | INCOMPLETE | DONE | 4
| DAY 1 :The scheduled work was done | DAY 2: ONLY HALF OF THE SCHEDULED WORK IS DONE | DAY 1 :The scheduled work was done
| DAY 1: WE WENT OVER BUDGET: 61 euro | DAY 2: 30 euro was spent | DAY 3: 80 euro was spent

## CPI
if CPI is: |  | This means
Greater than 1 | > 1 | Cost is lower than budget = Good performance
Less than 1 | < 1 | Cost is higher than budget = Bad performance
Equal to 1 | = 1 | Project is according budget (on target)

## SPI
if SPI is: |  | This means
Greater than 1 | > 1 | Project is ahead of schedule = Good performance
Less than 1 | < 1 | Project is behind schedudule = Bad performance
Equal to 1 | = 1 | Project is on target (on schedule)

## CV
if SPI is: |  | This means
Positive | > 0 | Cost is less than budget: work is under budget (Good)
Negative | < 0 | Cost is more than budget: work is over budget (Bad)
Zero | = 0 | Cost is equal to budget: work is on budget

## SV
if SPI is: |  | This means
Positive | > 0 | Work is ahead of schedule (Good)
Negative | < 0 | Work is behind schedule (Bad)
Zero | = 0 | Work is on schedule