## SETTINGS
EARNED VALUE MANAGEMENT |  |  | SUPPORT
|  |  | v1 | ET0330012007001
|  |  | Product Page | Earned Value Management Template
https://indzara.com/2016/02/earned-value-management-free-excel-template/ |  |  | Site | www.indzara.com
|  |  | E-mail | indzara@gmail.com
|  |  | Password | indzara
PROJECT START DATE | 2020-05-11 | STEPS
PROJECT END DATE | 2020-06-15 | 1. Enter basic project information in SETTINGS
AGGREGATE | WEEKLY | 2. Enter Plan information in PLAN sheet
PLANNING UNIT | HOURS | 3. Enter Actual work performed in ACTUAL sheet
COST ENTRY | ACTUAL COST | 4. Enter Actual Cost in ACTUAL_COST sheet
CURRENCY | € | 5. View EVM sheet for the output calculations

## PLAN
PERIOD |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
ENTER PLANNED HOURS | WEEK END DATE --> | 1: 2020-05-17; 2: 2020-05-24; 3: 2020-05-31; 4: 2020-06-07; 5: 2020-06-14
TASK | COST PER HOUR | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12 | P13 | P14 | P15 | P16 | P17 | P18 | P19 | P20 | P21 | P22 | P23 | P24 | P25 | P26 | P27 | P28 | P29 | P30 | P31 | P32 | P33 | P34 | P35 | P36 | P37 | P38 | P39 | P40 | P41 | P42 | P43 | P44 | P45 | P46 | P47 | P48 | P49 | P50 | P51 | P52 | TOTAL
Task One | 5 | 1: 50; 2: 0; 3: 0; 4: 0; 5: 0; 6: 0; 7: 0; 8: 0; 9: 0; 10: 0 | 250
Task Two | 5 | 1: 0; 2: 50; 3: 0; 4: 0; 5: 0; 6: 0; 7: 0; 8: 0; 9: 0; 10: 0 | 250
Task Three | 5 | 1: 0; 2: 0; 3: 50; 4: 0; 5: 0; 6: 10; 7: 0; 8: 0; 9: 0; 10: 0 | 250

## ACTUAL
PERIOD |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
ENTER ACTUAL % OF WORK DONE | WEEK END DATE --> | 1: 2020-05-17; 2: 2020-05-24; 3: 2020-05-31; 4: 2020-06-07; 5: 2020-06-14
TASK | TOTAL % | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12 | P13 | P14 | P15 | P16 | P17 | P18 | P19 | P20 | P21 | P22 | P23 | P24 | P25 | P26 | P27 | P28 | P29 | P30 | P31 | P32 | P33 | P34 | P35 | P36 | P37 | P38 | P39 | P40 | P41 | P42 | P43 | P44 | P45 | P46 | P47 | P48 | P49 | P50 | P51 | P52
Task One | 100% | 1: 100%; 2: 0%; 3: 0%; 4: 0%; 5: 0%; 6: 0%
Task Two | 50% | 1: 0%; 2: 50%; 3: 0%; 4: 0%; 5: 0%; 6: 0%
Task Three | 150% | 1: 0%; 2: 0%; 3: 50%; 4: 100%; 5: 0%; 6: 0%

## ACTUAL_COST
PERIOD |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
ENTER ACTUAL COST | WEEK END DATE --> | 1: 2020-05-17; 2: 2020-05-24; 3: 2020-05-31; 4: 2020-06-07; 5: 2020-06-14
TASK | TOTAL | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12 | P13 | P14 | P15 | P16 | P17 | P18 | P19 | P20 | P21 | P22 | P23 | P24 | P25 | P26 | P27 | P28 | P29 | P30 | P31 | P32 | P33 | P34 | P35 | P36 | P37 | P38 | P39 | P40 | P41 | P42 | P43 | P44 | P45 | P46 | P47 | P48 | P49 | P50 | P51 | P52
Task One | 61 | 1: 61; 2: 0; 3: 0; 6: 0
Task Two | 30 | 1: 0; 2: 30; 3: 0; 4: 0; 5: 0; 6: 0
Task Three | 80 | 1: 0; 2: 0; 3: 80; 4: 0; 6: 0

## H_CALC (hidden)
Number of columns of valid dates - used in snapshot dates data validation
5
| 2020-05-10 | 2020-05-17 | 2020-05-24 | 2020-05-31 | 2020-06-07 | 2020-06-14 | 2020-06-21 | [46 empty] | TOTAL
| PLANNED | 250 | 250 | 250 | 0 | 0 | 50 | [46 empty] | 800
| EARNED | 250 | 125 | [50 empty] | 375
| ACTUAL COST | 61 | 30 | [50 empty] | 91
CUMULATIVE | PLANNED VALUE | 250 | 500 | 750 | 750 | 750 | 800 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| EARNED VALUE | 250 | 375 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| ACTUAL COST | 61 | 91 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| DATE | 2020-05-17 | 2020-05-24
| CPI | 4.0984 | 4.1209
| SPI | 1 | 0.75
| AS OF SNAPSHOT DATE | 2020-05-24
| SNAPSHOT PERIOD | 2
| PLANNED VALUE | 500
| EARNED VALUE | 375
| ACTUAL COST | 91
| SCHEDULE VARIANCE | -125
| COST VARIANCE | 284

## EVM
SNAPSHOT DATE | 2020-05-24
|  | VARIANCES |  |  | FORECASTING
PROJECT START DATE | 2020-05-11 | SCHEDULE VARIANCE (SV) | -125 | BEHIND SCHEDULE | METHOD | CPI
PROJECT END DATE | 2020-06-15 | COST VARIANCE (CV) | 284 | UNDER PLANNED COST | ESTIMATE TO COMPLETE (ETC) | 103.1333
PLANNED VALUE (PV) | 500 |  |  |  | ESTIMATE AT COMPLETION (EAC) | 194.1333
EARNED VALUE (EV) | 375 | INDICES |  |  | VARIANCE AT COMPLETION (VAC) | 605.8667
ACTUAL COST (AC) | 91 | SCHEDULE PERFORMANCE INDEX (SPI) | 0.75
BUDGET AT COMPLETION (BAC) | 800 | COST PERFORMANCE INDEX (CPI) | 4.1209 |  | ESTIMATED COMPLETION DATE | 2020-06-26 16:00
TO-COMPLETE PERFORMANCE INDEX (TCPI)
|  | Option 1: To Complete On Planned Budget | 0.59944 | EASIER TO COMPLETE
|  | Option 2: To Complete on new EAC Budget | 4.1209 | HARDER TO COMPLETE
Note on E5: indzara: SV = EV - PV
Note on E6: indzara: CV = EV - AC
Note on E9: indzara: SPI = EV / PV
Note on E10: indzara: CPI = EV / AC
Note on E12: indzara: TCPI = (BAC - EV) / (BAC - AC)
Note on E13: indzara: TCPI = (BAC - EV) / (EAC - AC)

## TERMS
TERM | ABBREVIATION | DEFINITION | NOTES
PLANNED VALUE | PV | Authorized Budget assigned to the scheduled work | Also called as Budgeted Cost for Work Scheduled (BCWS)
EARNED VALUE | EV | Measure of actual work performed expressed as budget authorized for that work | Also called as Budgeted Cost for Work Performed (BCWP)
ACTUAL COST | AC | Actual cost incurred for the work performed | Also called as Actual Cost of Work Performed (ACWP)
SCHEDULE VARIANCE | SV | Amount by which project is ahead or behind plan | = EV - PV
COST VARIANCE | CV | Amount by which actual cost is ahead or behind planned cost | = EV - AC
BUDGET AT COMPLETION | BAC | Total Budget assigned to the entire plan
SCHEDULE PERFORMANCE INDEX | SPI | Measure of Schedule efficiency expressed as Earned Value to Planned Value | = EV/PV
COST PERFORMANCE INDEX | CPI | Measure of Cost efficiency expressed as Earned Value to Actual Cost | = EV/AC
ESTIMATE AT COMPLETION | EAC | Expected Total Cost of project = sum of Actual Cost till date and Estimate To Complete remaining work Option 1) Remaining Work will be done at the planned/budgeted rate Option 2) Remaining Work will be done at the present CPI Option 3) Remaining Work will be done considering present SPI and CPI | Option 1) = AC + (BAC - EV) Option 2) = BAC/CPI Option 3) = AC + [(BAC- EV)/(CPI * SPI)]
ESTIMATE TO COMPLETE | ETC | Expected Cost to finish the remaining project work | = EAC - AC
VARIANCE AT COMPLETION | VAC | Estimated difference in cost at the completion of the project compared to Plan | = BAC - EAC
TO-COMPLETE PERFORMANCE INDEX | TCPI | Measure of the cost performance required with the remaining resources to meet goal. Work Remaining/Funds Remaining Option 1) Efficiency that must be maintained to complete on Planned Budget Option 2) Efficiency that must be maintained to complete on current EAC | Option 1) = (BAC- EV)/(BAC- AC) Option 2) = (BAC- EV)/(EAC- AC)
ESTIMATED COMPLETION DATE | ECD | Expected Completion Date of the project | = Project Start Date + (Planned Duration/SPI)