## VoorbeeldEV
| Voorbeeld Earned Value Management |  |  |  | https://www.youtube.com/watch?v=sEju-I_sXlM&list=PL13IJTeX9RPWIdvbVjOBthLtZe_hbMws5&index=12 | [5 empty] | END OF DAY 1
| DAY 1 BUDGET = 50 euro | DAY 1 BUDGET = 50 euro | DAY 1 BUDGET = 50 euro | DAY 1 BUDGET = 50 euro | Total Budget for the project is 200 euro | BAC (Budget At Completion) |  |  |  |  | DAY 1 budget = 50 euro | DAY 1 budget = 50 euro | DAY 1 budget = 50 euro | DAY 1 budget = 50 euro | TOTAL BUDGET FOR THE PROJECT IS 200 EURO
| 25 | 25 | 25 | 25 | [6 empty] | DONE | DONE | DONE | 4
| 25 | 25 | 25 | 25 | [6 empty] | DONE | INCOMPLETE | DONE | 4
| voorbeeld = wall painting in yellow, green, pink and blue | [9 empty] | DAY 1 :The scheduled work was done | DAY 2: ONLY HALF OF THE SCHEDULED WORK IS DONE | DAY 1 :The scheduled work was done
| PV |  | EV | AC | [6 empty] | DAY 1: WE WENT OVER BUDGET: 61 euro | DAY 2: 30 euro was spent | DAY 3: 80 euro was spent
| The value of work scheduled to be done within a SPECIFIC time period | % COMPLETE the amount of work actually completed | The value of work accomplished within the specific time period | How much I paid for the work accomplished within the specific time period | CPI (EV/AC) | SPI (EV/PV) | CV (EV-AC) | SV (EV-PV) |  |  | EV na 1 dag= | % completed x PV
DAY 1 | 50 | 100% | 50 | 61 | 0.81967 | 1 | -11 | 0 |  | EV na 1 dag
DAY 2 | 50 | 50% | 25 | 30 | 0.83333 | 0.5 | -5 | -25
CUMULATIEF NA 2e dag | 100 | 0.75 | 75 | 91 | 0.82418 | 0.75 | -16 | -25 | NA 2 DAGEN
| EAC1 | 216 | optimistische schatting van de totale kost om het project volledig af te werken, gebaseerd op situatie na 2 dagen,
met de veronderstelling dat Jantje het werk nog volgens de voorziene budget voor de 2 volgende dagen kan afwerken
| EAC2 | 242.6667
| EAC3 | 293.2222
| EAC4 | 323.5556

## CPI
if CPI is: |  | This means
Greater than 1 | > 1 | Cost is lower than budget = Good performance
Less than 1 | < 1 | Cost is higher than budget = Bad performance
Equal to 1 | = 1 | Project is according budget (on target)

## SPI
if SPI is: |  | This means
Greater than 1 | > 1 | Project is ahead of schedule = Good performance
Less than 1 | < 1 | Project is behind schedudule = Bad performance
Equal to 1 | = 1 | Project is on target (on schedule)

## CV
if CV is: |  | This means
Positive | > 0 | Cost is less than budget: work is under budget (Good)
Negative | < 0 | Cost is more than budget: work is over budget (Bad)
Zero | = 0 | Cost is equal to budget: work is on budget

## SV
if SV is: |  | This means
Positive | > 0 | Work is ahead of schedule (Good)
Negative | < 0 | Work is behind schedule (Bad)
Zero | = 0 | Work is on schedule