## SETTINGS
EARNED VALUE MANAGEMENT |  |  | SUPPORT
|  |  | v1 | ET0330012007001
|  |  | Product Page | Earned Value Management Template
|  |  | Site | www.indzara.com
|  |  | E-mail | indzara@gmail.com
|  |  | Password | indzara
PROJECT START DATE | 2020-01-01 | STEPS
PROJECT END DATE | 2020-10-31 | 1. Enter basic project information in SETTINGS
AGGREGATE | MONTHLY | 2. Enter Plan information in PLAN sheet
PLANNING UNIT | HOURS | 3. Enter Actual work performed in ACTUAL sheet
COST ENTRY | COST CHANGE | 4. Enter Actual Cost in ACTUAL_COST sheet
CURRENCY | € | 5. View EVM sheet for the output calculations

## PLAN
PERIOD |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
ENTER PLANNED HOURS | MONTH END DATE--> | 2020-01-31 | 2020-02-29 | 2020-03-31 | 2020-04-30 | 2020-05-31 | 2020-06-30 | 2020-07-31 | 2020-08-31 | 2020-09-30 | 2020-10-31
TASK | COST PER HOUR | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12 | P13 | P14 | P15 | P16 | P17 | P18 | P19 | P20 | P21 | P22 | P23 | P24 | P25 | P26 | P27 | P28 | P29 | P30 | P31 | P32 | P33 | P34 | P35 | P36 | P37 | P38 | P39 | P40 | P41 | P42 | P43 | P44 | P45 | P46 | P47 | P48 | P49 | P50 | P51 | P52 | TOTAL
Task One | 10 |  | 50 | 50 | 50 | 20 | 50 | 50 | 75 | 75 | 100 | [42 empty] | 5200
Task Two | 20 | 10 | 25 | 25 | 25 | 50 | 10 | 5 | 40 | 45 | 20 | [42 empty] | 5100
Task Three | 25 | 5 | 10 | 50 | 10 | 10 | 10 | 50 | 40 | 25 | 250 | [42 empty] | 11500

## ACTUAL
PERIOD |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
ENTER ACTUAL % OF WORK DONE | MONTH END DATE--> | 2020-01-31 | 2020-02-29 | 2020-03-31 | 2020-04-30 | 2020-05-31 | 2020-06-30 | 2020-07-31 | 2020-08-31 | 2020-09-30 | 2020-10-31
TASK | TOTAL % | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12 | P13 | P14 | P15 | P16 | P17 | P18 | P19 | P20 | P21 | P22 | P23 | P24 | P25 | P26 | P27 | P28 | P29 | P30 | P31 | P32 | P33 | P34 | P35 | P36 | P37 | P38 | P39 | P40 | P41 | P42 | P43 | P44 | P45 | P46 | P47 | P48 | P49 | P50 | P51 | P52
Task One | 70% | 15% | 5% | 10% | 10% | 10% | 20%
Task Two | 75% | 20% | 5% | 5% | 20% | 5% | 20%
Task Three | 90% | 10% | 10% | 10% | 50% | 5% | 5%

## ACTUAL_COST
PERIOD |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
ENTER COST CHANGE | MONTH END DATE--> | 2020-01-31 | 2020-02-29 | 2020-03-31 | 2020-04-30 | 2020-05-31 | 2020-06-30 | 2020-07-31 | 2020-08-31 | 2020-09-30 | 2020-10-31
TASK | TOTAL | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12 | P13 | P14 | P15 | P16 | P17 | P18 | P19 | P20 | P21 | P22 | P23 | P24 | P25 | P26 | P27 | P28 | P29 | P30 | P31 | P32 | P33 | P34 | P35 | P36 | P37 | P38 | P39 | P40 | P41 | P42 | P43 | P44 | P45 | P46 | P47 | P48 | P49 | P50 | P51 | P52
Task One | 500 | 2020-01-31: 100; 2020-02-29: 200; 2020-03-31: -50; 2020-06-30: 250
Task Two | 625 | 100 | 50 | 200 | 50 | 75 | 150
Task Three | 945 | 2020-01-31: 500; 2020-02-29: 200; 2020-03-31: 25; 2020-04-30: 200; 2020-06-30: 20

## H_CALC (hidden)
Number of columns of valid dates - used in snapshot dates data validation
10
| 2019-12-31 | 2020-01-31 | 2020-02-29 | 2020-03-31 | 2020-04-30 | 2020-05-31 | 2020-06-30 | 2020-07-31 | 2020-08-31 | 2020-09-30 | 2020-10-31 | [42 empty] | TOTAL
| PLANNED | 325 | 1250 | 2250 | 1250 | 1450 | 950 | 1850 | 2550 | 2275 | 7650 | [42 empty] | 21800
| EARNED | 2950 | 1665 | 1925 | 7290 | 1350 | 2635 | [46 empty] | 17815
| ACTUAL COST | 1025 | 1700 | 2425 | 1500 | 1525 | 1370 | [46 empty] | 9545
CUMULATIVE | PLANNED VALUE | 325 | 1575 | 3825 | 5075 | 6525 | 7475 | 9325 | 11875 | 14150 | 21800 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| EARNED VALUE | 2950 | 4615 | 6540 | 13830 | 15180 | 17815 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| ACTUAL COST | 1025 | 2725 | 5150 | 6650 | 8175 | 9545 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| DATE | 2020-01-31 | 2020-02-29 | 2020-03-31 | 2020-04-30 | 2020-05-31 | 2020-06-30
| CPI | 2.878 | 1.6936 | 1.2699 | 2.0797 | 1.8569 | 1.8664
| SPI | 9.0769 | 2.9302 | 1.7098 | 2.7251 | 2.3264 | 2.3833
| AS OF SNAPSHOT DATE | 2020-06-30
| SNAPSHOT PERIOD | 6
| PLANNED VALUE | 7475
| EARNED VALUE | 17815
| ACTUAL COST | 9545
| SCHEDULE VARIANCE | 10340
| COST VARIANCE | 8270

## EVM
SNAPSHOT DATE | 2020-06-30
|  | VARIANCES |  |  | FORECASTING
PROJECT START DATE | 2020-01-01 | SCHEDULE VARIANCE (SV) | 10340 | AHEAD OF SCHEDULE | METHOD | CPI
PROJECT END DATE | 2020-10-31 | COST VARIANCE (CV) | 8270 | UNDER PLANNED COST | ESTIMATE TO COMPLETE (ETC) | 2135.101
PLANNED VALUE (PV) | 7475 |  |  |  | ESTIMATE AT COMPLETION (EAC) | 11680.101
EARNED VALUE (EV) | 17815 | INDICES |  |  | VARIANCE AT COMPLETION (VAC) | 10119.899
ACTUAL COST (AC) | 9545 | SCHEDULE PERFORMANCE INDEX (SPI) | 2.3833
BUDGET AT COMPLETION (BAC) | 21800 | COST PERFORMANCE INDEX (CPI) | 1.8664 |  | ESTIMATED COMPLETION DATE | 2020-05-07 13:20
TO-COMPLETE PERFORMANCE INDEX (TCPI)
|  | Option 1: To Complete On Planned Budget | 0.32517 | EASIER TO COMPLETE
|  | Option 2: To Complete on new EAC Budget | 1.8664 | HARDER TO COMPLETE
Note on E5: indzara: SV = EV - PV
Note on E6: indzara: CV = EV - AC
Note on E9: indzara: SPI = EV / PV
Note on E10: indzara: CPI = EV / AC
Note on E12: indzara: TCPI = (BAC - EV) / (BAC - AC)
Note on E13: indzara: TCPI = (BAC - EV) / (EAC - AC)

## TERMS
TERM | ABBREVIATION | DEFINITION | NOTES
PLANNED VALUE | PV | Authorized Budget assigned to the scheduled work | Also called as Budgeted Cost for Work Scheduled (BCWS)
EARNED VALUE | EV | Measure of actual work performed expressed as budget authorized for that work | Also called as Budgeted Cost for Work Performed (BCWP)
ACTUAL COST | AC | Actual cost incurred for the work performed | Also called as Actual Cost of Work Performed (ACWP)
SCHEDULE VARIANCE | SV | Amount by which project is ahead or behind plan | = EV - PV
COST VARIANCE | CV | Amount by which actual cost is ahead or behind planned cost | = EV - AC
BUDGET AT COMPLETION | BAC | Total Budget assigned to the entire plan
SCHEDULE PERFORMANCE INDEX | SPI | Measure of Schedule efficiency expressed as Earned Value to Planned Value | = EV/PV
COST PERFORMANCE INDEX | CPI | Measure of Cost efficiency expressed as Earned Value to Actual Cost | = EV/AC
ESTIMATE AT COMPLETION | EAC | Expected Total Cost of project = sum of Actual Cost till date and Estimate To Complete remaining work Option 1) Remaining Work will be done at the planned/budgeted rate Option 2) Remaining Work will be done at the present CPI Option 3) Remaining Work will be done considering present SPI and CPI | Option 1) = AC + (BAC - EV) Option 2) = BAC/CPI Option 3) = AC + [(BAC- EV)/(CPI * SPI)]
ESTIMATE TO COMPLETE | ETC | Expected Cost to finish the remaining project work | = EAC - AC
VARIANCE AT COMPLETION | VAC | Estimated difference in cost at the completion of the project compared to Plan | = BAC - EAC
TO-COMPLETE PERFORMANCE INDEX | TCPI | Measure of the cost performance required with the remaining resources to meet goal. Work Remaining/Funds Remaining Option 1) Efficiency that must be maintained to complete on Planned Budget Option 2) Efficiency that must be maintained to complete on current EAC | Option 1) = (BAC- EV)/(BAC- AC) Option 2) = (BAC- EV)/(EAC- AC)
ESTIMATED COMPLETION DATE | ECD | Expected Completion Date of the project | = Project Start Date + (Planned Duration/SPI)